## Prioritized_Improvements
Issue ID | Stakeholder Evidence | Identified Problem | Severity | Priority | Effort | Proposed / Implemented Change | Verification Method | Status
IMP-01 | User Riddhi & screenshot media_18ae0c6b.png | White text rendering on light background when mobile/OS is in dark mode. | High | Critical | Low | Enforced light theme in .streamlit/config.toml and forced dark navy text via !important CSS. | Visual audit on mobile device with dark mode enabled. | Implemented (P2)
IMP-02 | User Siddhi & Tharun | Initial question bank had only 24 questions (2 per topic), insufficient for exam prep. | High | High | Medium | Expanded question bank to exactly 12 questions in EVERY topic (144 questions total). | Automated validation in test_medskill.py asserting 12 per topic. | Implemented (P2)
IMP-03 | User Naziya & clinical instructors | Examiners conduct verbal vivas, but application only offered multiple-choice options. | Medium | High | Medium | Engineered 'Quick Viva Mode' allowing students to type answers and compare against reference model. | Usability test with 5 students comparing against instructor standard. | Implemented (P2)
IMP-04 | User Bhargav & Atharv | Users had to restart entire quiz to review 2 missed questions; no targeted retry. | Medium | High | Low | Added 1-click '⚡ Quick Retry Quiz' button that filters active set to only missed questions. | Functional test verifying active list length matches missed count. | Implemented (P2)
IMP-05 | User Preethi | Next Question button rendered beside Check Answer above the explanation, causing confusion. | Medium | Medium | Low | Relocated Next Question button below feedback and expander card with vibrant blue styling. | Layout audit ensuring logical top-to-bottom reading sequence. | Implemented (P2)
IMP-06 | User Naveen (ICU posting) | Hospital basements have no mobile reception; app crashed if API key missing. | High | Critical | Medium | Built local semantic keyword retrieval fallback in query_optional_ai() with zero crash risk. | Executed app without GEMINI_API_KEY and verified response. | Implemented (P2)
IMP-07 | User Tharun | First-year juniors found advanced ventilator equations intimidating without difficulty guidance. | Low | Medium | Low | Added Beginner, Intermediate, and Advanced difficulty badges and filter dropdown. | Tested difficulty filtering across all 3 specialties. | Implemented (P2)
IMP-08 | User Atharv | Students needed concise bullet points rather than long paragraphs right before entering viva. | Low | Medium | Low | Added expandable '📌 Key Viva Revision Points' card to every single question. | Verified all 144 questions contain >= 3 bullet points. | Implemented (P2)
IMP-09 | Proposed (Future Phase) | Students cannot track long-term improvement across multiple days without login. | Low | Low | High | Introduce optional local browser localStorage or lightweight SQLite profile persistence. | User study measuring retention over 14-day study period. | Proposed (P3)
IMP-10 | Proposed (Future Phase) | Students wish to speak oral answers instead of typing on mobile keypad. | Low | Low | High | Integrate browser Web Speech API for voice-to-text dictation in Quick Viva mode. | Speech accuracy test in hospital environment with ambient noise. | Proposed (P3)